## EITI Plan of Activities
WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE - ANGOLA (2022-2024)
Objective | General EITI Requirements | Overall output | Expected Output | Activity |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | Responsible entity | Responsible | Budget allocation (USD) | Source of Financing
[6 empty] | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Create technical and operational capacity of the National Coordination Committee and National Secretariat to ensure viable effective implementation of the EITI in Angola | Requirement 1. Effective oversight by the Multi-Stakeholder Group involved. The principal elements related to oversight by the multi-stakeholder group include (The EITI requires effective oversight by the various parties) : (1.1) government engagement; (1.2) engagement of companies; (1.3) engagement of civil society ; (1.4) establishment and functioning of a multi-stakeholder group; and (1.5) a work plan agreed with clear objectives for the implementation of the EITI and a timetable aligned with the time limits established by the EITI Management Board) | Ensure government commitment and engagement of civil society, establishment and functioning of a multi-stakeholder group, an agreed workplan, clear objectives and a realistic timetable, aligned with the time limits established by the EITI Board and increase the knowledge of members of the MSG | Output - Government commitment to the EITI principles and standards | 1 | Statement by His Excellency, the President of the Republic of Angola expressing his interest in adhesion to the EITI | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 1 Quarter Feb; 1 Quarter Jan
|  |  |  | 2 | Opening ceremony of the new MSG | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 1 Quarter Mar; 1 Quarter Mar
|  |  |  | 3 | Publication of list of the new members of the MSG as signatories (post-election) | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 2 Quarter Apr; 1 Quarter Mar
|  |  |  | 4 | Signing of Memorandum of Understanding between the Government stakeholders on the implementation of the EITI | [48 empty] | NCC(MSG) Secretariat | CNC/GOV | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Feb
|  |  |  | 5 | Annual quota to the EITI International Secretariat | [48 empty] | NCC(MSG) Secretariat |  | 30000 | General State Budget | bar: 1 Quarter Feb; 1 Quarter Feb; 1 Quarter Feb
|  |  | Output-Create operational, administrative and organizational procedures of the EITI-AO | 6 | Constitution of the EITI-AO National Secretariat | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 7 | Creation of the functional structure of the administrative organization of the NCC, with rules of procedure | [48 empty] | NCC(MSG) Secretariat | CNC | 65254 | General State Budget | bar: 3 Quarter July; 3 Quarter July; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 8 | Technical resources, logistical support for the functioning of the NCC Secretariat | [48 empty] | NCC(MSG) Secretariat |  | 254876.98 | General State Budget | bar: 3 Quarter July; 2 Quarter Jun; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 9 | Logistical support for the holding of meetings and travel within Angola | [48 empty] | NCC(MSG) Secretariat |  | 32987.68 | Other voluntary funding sources | bar: 3 Quarter July; 2 Quarter Jun; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 10 | Provision of administrative service to support the functioning of the NCC Secretariat | [48 empty] | NCC(MSG) Secretariat |  | 288000 | General State Budget | bar: 3 Quarter July to 4 Quarter Dec
|  |  |  | 11 | Definition of the financing model for activities to be executed by the NCC, including mapping of sources of financing | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 12 | Elaboration and update of the Terms of Reference on the National Secretariat | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan; 1 Quarter Feb
|  |  |  | 13 | Consultation and approval of the operational documents and procedures by the MSG | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan; 1 Quarter Jan
|  |  |  | 14 | Mapping of the MSG member base (level of entity) and disclosure (Private Sector, Government and CSOs) | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 3 Quarter Sep; 1 Quarter Mar
|  |  |  | 15 | Ensure and support CSOs and the private sector in the development of transparent electoral procedures | [48 empty] | NCC/Private Sector /CSO Secretariat | CNC/SP/OSC | 8760 | Other voluntary funding sources | bar: 2 Quarter May; 1 Quarter Jan
|  |  |  | 16 | Holding of elections for the industry and civil society and present the Government representatives | [48 empty] | CSO & Private Sector | OSC & SP | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Jan to 1 Quarter Feb
|  |  |  | 17 | Monitoring of the electoral process, registration and publication of the process | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Jan to 1 Quarter Feb
|  |  |  | 18 | Nomination of the NCC (MSG), Chairperson and Executive Director | [48 empty] | GOV | GOV | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Mar
|  |  |  | 19 | Identifying of new members of the Working Group | [48 empty] | NCC(MSG) Secretariat | MSG | 0 | General State Budget | bar: 1 Quarter Mar
|  |  | Output - Strengthening of knowledge base, capacity and skills of EITI-AO MSG on the functioning of the EITI | 20 | Induction training on key question of implementation of the EITI (taxation, fiscal regime , etc.) | [48 empty] | NCC(MSG) Secretariat | CNC | 45386 | General State Budget | bar: 1 Quarter Mar; 1 Quarter Feb to 1 Quarter Mar
|  |  |  | 21 | Exchange of experiences with other EITI implementing countries (e.g.. Mozambique) | [48 empty] | NCC(MSG) Secretariat | CNC | 37976 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar
|  |  |  | 22 | Participation of the NCC ( MSG) on the Oil and Gas Mining Conference (INDABA 2022-2023) | [48 empty] | NCC(MSG) Secretariat | CNC | 28765 | General State Budget | bar: 1 Quarter Feb; 2 Quarter May
|  |  |  | 23 | Organization of strategic meetings for members of the MSG, to promote better coordination and information flows. | [48 empty] | NCC(MSG) Secretariat | MSG | 3587 | Other voluntary funding sources | bar: 3 Quarter July; 2 Quarter Apr; 3 Quarter Sep
|  |  |  | 24 | Conduct of a study to identify possible obstacles to the implementation of the EITI in Angola and strategies to mitigate risks | [48 empty] | NCC(MSG) Secretariat | MSG | 53987 | General State Budget | bar: 2 Quarter Apr; 2 Quarter May; 3 Quarter July; 3 Quarter Sep
|  |  | Output - Annual work plan of the MSG | 25 | Elaboration of Annual Plans of Activities for the triennium 2021 - 2023 | [48 empty] | NCC(MSG) | MSG | 1575 | Other funding sources | bar: 1 Quarter Jan to 1 Quarter Mar; 2 Quarter Jun; 4 Quarter Oct
|  |  |  | 26 | Annual Report of Activities 2021 and elaboration of the Annual Plan 2022 | [48 empty] | NCC(MSG | MSG | 12876.9 | Other voluntary funding sources | bar: 2 Quarter Jun; 4 Quarter Oct
|  |  |  | 27 | Annual Report of Activities 2022 and elaboration of the Annual Plan 2023 | [48 empty] | NCC(MSG | MSG | 1757 | Other voluntary funding sources | bar: 3 Quarter Sep to 4 Quarter Oct
|  |  |  | 28 | Annual Report of Activities 2023 | [48 empty] | NCC(MSG | MSG | 1757 | Other voluntary funding sources | bar: 4 Quarter Nov
|  |  | Output - Angola's candidature prepared | 29 | Preparation for submission of the Candidature to the EITI International Board | [48 empty] | NCC(MSG | CNC | 0 | General State Budget | bar: 1 Quarter Mar
|  |  |  | 30 | Organization of supporting documentation to be annexed to Angola's candidature for the EITI to be presented to the MSG | [48 empty] | NCC(MSG | MSG | 0 | General State Budget | bar: 1 Quarter Feb to 2 Quarter Apr
|  |  |  | 31 | Submission of candidature to the EITI International Board | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 1 Quarter Mar to 2 Quarter Apr
|  |  | Output - Timely publication of the annual reports of the EITI-AO based on the EITI requirements. | 32 | Conduct of training for the Secretariat and the Independent Administrator on planning and delivery of Requirement 4 - Design and conclusion of formats of reports and preparation of the first EITI-AO Report | [48 empty] | NCC(MSG) Secretariat) | CNC | 22346 | General State Budget | bar: 2 Quarter May; 1 Quarter Jan to 1 Quarter Feb
|  |  |  | 33 | Contracting and appointment of the Independent Administrator for the 1st EITI-AO Report | [48 empty] | NCC(MSG) Secretariat) | CNC | 185600 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan to 1 Quarter Mar
|  |  |  | 34 | Contracting of technical, legal and communication consultant | [48 empty] | NCC(MSG) Secretariat |  | 120567 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan to 1 Quarter Mar
|  |  |  | 35 | Training for companies, Government and members of the MSG involved in payments and collection of revenues on models for completion of date to be included in the EITI-AO Report | [48 empty] | AWG/CNC | AWG/CNC | 64000 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar
|  |  |  | 36 | Exchange visit to the EITI International Secretariat | [48 empty] | NCC(MSG) Secretariat) | CNC | 54398 | General State Budget | bar: 1 Quarter Mar; 3 Quarter Aug; 1 Quarter Mar
|  |  |  | 37 | Presentation, approval and publication of the first EITI-AO Report to the MSG and through briefings/news | [48 empty] | NCC(MSG | MSG | 35200 | General State Budget | bar: 4 Quarter Oct
|  |  |  | 38 | Printing and distribution of the 1st EITI-AO Report | [48 empty] | NCC(MSG) Secretariat | CNC | 13987 | General State Budget | bar: 4 Quarter Nov to 4 Quarter Dec
|  |  |  | 39 | Workshop on lessons to be learned from the 1st EITI-AO Report ( for the relevant stakeholders) | [48 empty] | NCC(MSG | MSG | 26098 | General State Budget | bar: 4 Quarter Nov
|  |  | Output - meetings held throughout the three years. | 40 | Holding of quarterly meetings of the MSG (minimum eight) for evaluation of progress of activities and monitoring the overall performance of the implementation of the EITI in Angola | [48 empty] | NCC(MSG | MSG | 16987 | General State Budget | bar: 1 Quarter Jan; 2 Quarter Apr; 3 Quarter July; 4 Quarter Oct; 1 Quarter Jan; 2 Quarter Jun; 3 Quarter Sep; 4 Quarter Dec; 1 Quarter Mar; 2 Quarter Jun; 4 Quarter Oct to 4 Quarter Nov
|  |  |  | 41 | Organization of field visits to the extractive regions for members of the MSG Secretariat | [48 empty] | NCC(MSG | CNC | 18609 | General State Budget | bar: 1 Quarter Jan; 2 Quarter Apr; 3 Quarter July; 4 Quarter Oct; 1 Quarter Jan; 2 Quarter Jun; 3 Quarter Sep; 4 Quarter Dec; 1 Quarter Mar; 2 Quarter Jun; 4 Quarter Oct to 4 Quarter Nov
Enhance and strengthen transparency of management of revenues from the extractive sector, improve the legal and institutional framework and the process of granting contracts and licences | Requirement 2 Legal and institutional framework, including granting of contracts and licences. (The EITI requirements on transparency of the legal framework and grant of rights of the extractive industries include: (2.1) legal and tax regime; (2.2) grant of contracts and licences; (2.3) register of licences; (2.4) contracts; (2.5) beneficial owners; and (2.6) state participation in the extractive sector.) | Disclosure of how the Extractive Sector is managed, allowing stakeholders to understand the laws and procedures for the allocation of exploration and production rights, the legal, regulatory and contractual framework applicable to the extractive sector and the institutional responsibilities of the State for management of revenues collected from the sector. | Output - Analysis of gaps, legal, regulatory and policy frameworks. | 42 | Investigation, analysis and presentation of information relevant for the Study of the Scope of the Legal Framework and Fiscal Regime, both for mining and oil and gas in Angola, and presentation of the conclusions to the MSG and other key stakeholders (identified). | [48 empty] | Technical Working Group | MSG | 123654 | Other voluntary funding sources | bar: 2 Quarter May to 3 Quarter July; 3 Quarter July
|  |  |  | 43 | Publication of legal, regulatory and policy changes in the EITI-AO website | [48 empty] | NCC(MSG) Secretariat | CNC | 15765 | Other voluntary funding sources | bar: 1 Quarter Mar; 2 Quarter Jun; 3 Quarter Sep; 4 Quarter Dec to 4 Quarter Dec
|  |  | Output - Plan published for the disclosure of contracts and licences and information on beneficial owners. | 44 | Development of a plan for disclosure of contracts, licences and their respective addendums in force in the extractive industries, and information on beneficial owners, in conjunction with Government entities. | [48 empty] | NCC(MSG) Secretariat) | CNC | 57987.91 | General State Budget | bar: 2 Quarter May to 2 Quarter Jun
|  |  |  | 45 | Workshop to present the results | [48 empty] | NCC(MSG) Secretariat | CNC | 12760 | Other voluntary funding sources | bar: 3 Quarter Aug; 4 Quarter Nov
| Requirement 3. Exploration and production. (The EITI requires disclosure of information related to exploration and production, allowing the stakeholders to understand the sector's potential.) | Enhance transparency in order to map operators and investments.
|  |  | Output - Ensuring collection of current data on production, consumption and exports. | 46 | Mapping of production, consumption and export data (oil, gas and mining), including analysis of the creation of a policy on data publication. | [48 empty] | Technical Working Group/Companies in Sector | CNC | 0 | Other voluntary funding sources | bar: 1 Quarter Jan
|  |  |  | 47 | Publication of production, consumption and export data for the triennium 2021- 2023 | [48 empty] | NCC Secretariat/Companies in Sector | CNC | 0 | Other voluntary funding sources | bar: 1 Quarter Feb; 3 Quarter Aug
Promote the public disclosure of taxes, levies and contributions of the extractive sector, including profits and the process of transfer of revenues to the host communities | Requirement 4. Collection of revenues. (The EITI requires disclosure covering payments of companies and government revenues derived from from the extractive industries) | Publication of information on taxes, levies and contributions collected by the State in the sector, including State participation through state enterprises.
|  |  | Output - Study of the scope of revenues collected in preparation for the first EITI-AO Report. | 48 | Development of Terms of Reference for the Independent Administrator | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 3 Quarter Aug to 4 Quarter Oct; 1 Quarter Mar
|  |  |  | 49 | Determination of total revenues of extractive operators to be included in the EITI-AO Report, including breakdown of amounts received and definition of the level of materiality | [48 empty] | Technical Working Group | MSG | 0 | General State Budget | bar: 2 Quarter Apr
|  |  |  | 50 | Presentation of the results and validation together with the MSG | [48 empty] | NCC(MSG) | MSG | 12754 | General State Budget | bar: 2 Quarter Apr
|  |  | Output - Institutionalize the systematic disclosure of data. | 51 | Development of a plan for disclosure of beneficial owners, together with the private sector | [48 empty] | Technical Working Group | CNC | 120324 | General State Budget | bar: 3 Quarter Aug
|  |  |  | 52 | Creation and mapping of the Flexible Register of Extractive Industries and Definition of the Aggregator/Data Regulator/Information Platform | [48 empty] | Technical Working Group | CNC | 349566.9 | General State Budget | bar: 3 Quarter Aug to 4 Quarter Dec
|  |  |  | 53 | Conduct of a study on the participation of state-owned enterprises in the mining and oil sector, including rules and practices prevailing between the Government and state-owned enterprises covering financing and governance. | [48 empty] | NCC(MSG) | MSG | 75765 | Other voluntary funding sources | bar: 4 Quarter Oct
|  |  |  | 54 | Production of reports on the annual audit of results and the impact of implementation of the EITI on the management of mining and oil resources in Angola, including the degree of compliance with the requirements of the EITI Standard | [48 empty] | NCC(MSG) |  | 90234 | General State Budget | bar: 4 Quarter Oct
|  |  |  | 55 | Promotion of systematic publication of data in the EITI-AO reports, in an online open data format, making them understandable and accessible to all | [48 empty] | GOV | GOV | 80987 | General State Budget | bar: 2 Quarter Apr
| Requirement 5. Allocation of revenues. (The requirements related to allocation of revenues include: (5.1) distribution of revenues; (5.2) subnational transfers; and (5.3) management of revenues and expenditures) | Improve knowledge of the benefits obtained by citizens as a result of investment in the extractive industries, ensure greater access to information on the EITI-AO.
|  |  | Output - Ensure collection of data related to allocation of revenues for systematic disclosure. | 56 | Monitoring of the process of collection of data on revenues from operations of the extractive industries for the EITI-AO Report, including any subnational payments (e.g. local royalties). | [48 empty] | NCC Secretariat | CNC | 0 | General State Budget | bar: 2 Quarter Apr
| Requirement 6. Social and economic expenditures (The requirements related to allocation of revenues include: (6.1) social and environmental expenditures of companies; (6.2) tax-equivalent expenses of state enterprises; (6.3) overview of the contribution of the extractive industries to the economy; and (6.4) environmental impact of extractive activities) |  | Output - Better awareness of the impacts of the extractive industries leading to better management and accountability for the social and environmental impacts by those responsible. | 57 | Disclosure of social and environmental expenditures of the extractive companies, through the EITI-AO Report (capture of "material", social and environmental to communities and to the Government, and information on expenditures related to social responsibility and remedial programmes, including "Persons affected by the project" (resettlement, etc.) | [48 empty] | Independent Administrator | AI | 0 | General State Budget | bar: 2 Quarter Apr
|  |  |  | 58 | Elaboration of a study on energy transition, a concept which has the purpose of replacing the use of finite sources prejudicial to the environment, such as fossil fuels, with renewable sources, such as solar, biogas. and wind. | [48 empty] | Ministry of Energy, MCTA |  | 15876.98 | Other voluntary funding sources | bar: 2 Quarter Apr
|  |  |  | 59 | Analysis of the contribution of the extractive sector to the economy (for example, size of the extractive sect-or in relation to GDP and the rest of the economy, revenues, exports and employment generated in absolute and relative terms (%); and monitoring of the activity to develop "contribution monitoring tool" to see of the extractive contribution is as expected. | [48 empty] | Independent Administrator | AI | 0 | General State Budget | bar: 1 Quarter Mar to 2 Quarter Apr
| Requirement 7. Outcomes and impact. 7.1 Public debate |  | Output- Ensure management of the expectations of the population and society at large, and better accountability for the management of revenues from the sector. | 60 | Publication of the results and recommendations of the EITI-AO Report to society and use of social communication media. Publication of the first EITI-AO Report. | [48 empty] | CSO | OSC | 40987 | General State Budget | bar: 2 Quarter Apr to 4 Quarter Dec
|  |  | Output - Conduct of four field visits | 61 | Publication of the results and recommendations of the EITI-AO Report to communities where the projects are located. | [48 empty] | CSO | OSC | 190254 | Other voluntary funding sources | bar: 2 Quarter Apr; 4 Quarter Nov to 4 Quarter Dec
| 7.2 Accessibility of data and open data |  | Output- Improve the level of access to information in the extractive sector in Angola. | 62 | Definition of the NCC Communication Policy (creation of scope of the EITI-AO, to facilitate communication, creation of logo) | [48 empty] | NCC(MSG) Secretariat) | CNC | 97468.98 | Other voluntary funding sources | bar: 2 Quarter Apr
|  |  |  | 63 | Creation, maintenance and update of EITI-AO website | [48 empty] | NCC(MSG) Secretariat) | CNC | 346127.98 | Other voluntary funding sources | bar: 4 Quarter Nov
TOTAL BUDGET | [55 empty] | 3055850.31
Test Marie | [55 empty] | 0
Note on AQ3: beatriz catomi:
Note on C7: beatriz catomi:

## Objective 1
WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE - ANGOLA (2022-2024)
OBJECTIVE Nº 1: Create technical and operational capacity of the National Coordination Committee and National Secretariat to ensure viable effective implementation of the EITI in Angola
Objective | General EITI Requirements | Overall output | Expected Output | Activity |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | Responsible entity | Responsible | Budget allocation (USD) | Source of Financing
[6 empty] | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Create technical and operational capacity of the National Coordination Committee and National Secretariat to ensure viable effective implementation of the EITI in Angola | Requirement 1. Effective oversight by the Multi-Stakeholder Group involved. The principal elements related to oversight by the multi-stakeholder group include (The EITI requires effective oversight by the various parties) : (1.1) government engagement; (1.2) engagement of companies; (1.3) engagement of civil society ; (1.4) establishment and functioning of a multi-stakeholder group; and (1.5) a work plan agreed with clear objectives for the implementation of the EITI and a timetable aligned with the time limits established by the EITI Management Board) | Ensure government commitment and engagement of civil society, establishment and functioning of a multi-stakeholder group, an agreed workplan, clear objectives and a realistic timetable, aligned with the time limits established by the EITI Board and increase the knowledge of members of the MSG | Output - Government commitment to the EITI principles and standards | 1 | Statement by His Excellency, the President of the Republic of Angola expressing his interest in adhesion to the EITI | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 1 Quarter Feb; 1 Quarter Jan
|  |  |  | 2 | Opening ceremony of the new MSG | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 1 Quarter Mar; 1 Quarter Mar
|  |  |  | 3 | Publication of list of the new members of the MSG as signatories (post-election) | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 2 Quarter Apr; 1 Quarter Mar
|  |  |  | 4 | Signing of Memorandum of Understanding between the Government stakeholders on the implementation of the EITI | [48 empty] | NCC(MSG) Secretariat | CNC/GOV | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Feb
|  |  |  | 5 | Annual quota to the EITI International Secretariat | [48 empty] | NCC(MSG) Secretariat |  | 30000 | General State Budget | bar: 1 Quarter Feb; 1 Quarter Feb; 1 Quarter Feb
|  |  | Output-Create operational, administrative and organizational procedures of the EITI-AO | 6 | Constitution of the EITI-AO National Secretariat | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 7 | Creation of the functional structure of the administrative organization of the NCC, with rules of procedure | [48 empty] | NCC(MSG) Secretariat | CNC | 65254 | General State Budget | bar: 3 Quarter July; 3 Quarter July; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 8 | Technical resources, logistical support for the functioning of the NCC Secretariat | [48 empty] | NCC(MSG) Secretariat |  | 254876.98 | General State Budget | bar: 3 Quarter July; 2 Quarter Jun; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 9 | Logistical support for the holding of meetings and travel within Angola | [48 empty] | NCC(MSG) Secretariat |  | 32987.68 | Other voluntary funding sources | bar: 3 Quarter July; 2 Quarter Jun; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 10 | Provision of administrative service to support the functioning of the NCC Secretariat | [48 empty] | NCC(MSG) Secretariat |  | 288000 | General State Budget | bar: 3 Quarter July to 4 Quarter Dec
|  |  |  | 11 | Definition of the financing model for activities to be executed by the NCC, including mapping of sources of financing | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar to 2 Quarter Apr
|  |  |  | 12 | Elaboration and update of the Terms of Reference on the National Secretariat | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan; 1 Quarter Feb
|  |  |  | 13 | Consultation and approval of the operational documents and procedures by the MSG | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan; 1 Quarter Jan
|  |  |  | 14 | Mapping of the MSG member base (level of entity) and disclosure (Private Sector, Government and CSOs) | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 3 Quarter Sep; 1 Quarter Mar
|  |  |  | 15 | Ensure and support CSOs and the private sector in the development of transparent electoral procedures | [48 empty] | NCC/Private Sector /CSO Secretariat | CNC/SP/OSC | 8760 | Other voluntary funding sources | bar: 2 Quarter May; 1 Quarter Jan
|  |  |  | 16 | Holding of elections for the industry and civil society and present the Government representatives | [48 empty] | CSO & Private Sector | OSC & SP | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Jan to 1 Quarter Feb
|  |  |  | 17 | Monitoring of the electoral process, registration and publication of the process | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Jan to 1 Quarter Feb
|  |  |  | 18 | Nomination of the NCC (MSG), Chairperson and Executive Director | [48 empty] | GOV | GOV | 0 | General State Budget | bar: 2 Quarter May; 1 Quarter Mar
|  |  |  | 19 | Identifying of new members of the Working Group | [48 empty] | NCC(MSG) Secretariat | MSG | 0 | General State Budget | bar: 1 Quarter Mar
|  |  | Output - Strengthening of knowledge base, capacity and skills of EITI-AO MSG on the functioning of the EITI | 20 | Induction training on key question of implementation of the EITI (taxation, fiscal regime , etc.) | [48 empty] | NCC(MSG) Secretariat | CNC | 45386 | General State Budget | bar: 1 Quarter Mar; 1 Quarter Feb to 1 Quarter Mar
|  |  |  | 21 | Exchange of experiences with other EITI implementing countries (e.g.. Mozambique) | [48 empty] | NCC(MSG) Secretariat | CNC | 37976 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar
|  |  |  | 22 | Participation of the NCC ( MSG) on the Oil and Gas Mining Conference (INDABA 2022-2023) | [48 empty] | NCC(MSG) Secretariat | CNC | 28765 | General State Budget | bar: 1 Quarter Feb; 2 Quarter May
|  |  |  | 23 | Organization of strategic meetings for members of the MSG, to promote better coordination and information flows. | [48 empty] | NCC(MSG) Secretariat | MSG | 3587 | Other voluntary funding sources | bar: 3 Quarter July; 2 Quarter Apr; 3 Quarter Sep
|  |  |  | 24 | Conduct of a study to identify possible obstacles to the implementation of the EITI in Angola and strategies to mitigate risks | [48 empty] | NCC(MSG) Secretariat | MSG | 53987 | General State Budget | bar: 2 Quarter Apr; 2 Quarter May; 3 Quarter July; 3 Quarter Sep
|  |  | output - Annual work plan of the MSG | 25 | Elaboration of Annual Plans of Activities for the triennium 2021 - 2023 | [48 empty] | NCC(MSG) | MSG | 1575 | Other funding sources | bar: 1 Quarter Jan to 1 Quarter Mar; 2 Quarter Jun; 4 Quarter Oct
|  |  |  | 26 | Annual Report of Activities 2021 and elaboration of the Annual Plan 2022 | [48 empty] | NCC(MSG | MSG | 12876.9 | Other voluntary funding sources | bar: 2 Quarter Jun; 4 Quarter Oct
|  |  |  | 27 | Annual Report of Activities 2022 and elaboration of the Annual Plan 2023 | [48 empty] | NCC(MSG | MSG | 1757 | Other voluntary funding sources | bar: 3 Quarter Sep to 4 Quarter Oct
|  |  |  | 28 | Annual Report of Activities 2023 | [48 empty] | NCC(MSG | MSG | 1757 | Other voluntary funding sources | bar: 4 Quarter Nov
|  |  | Output - Angola's candidature prepared | 29 | Preparation for submission of the Candidature to the EITI International Board | [48 empty] | NCC(MSG | CNC | 0 | General State Budget | bar: 1 Quarter Mar
|  |  |  | 30 | Organization of supporting documentation to be annexed to Angola's candidature for the EITI to be presented to the MSG | [48 empty] | NCC(MSG | MSG | 0 | General State Budget | bar: 1 Quarter Feb to 2 Quarter Apr
|  |  |  | 31 | Submission of candidature to the EITI International Board | [48 empty] | NCC(MSG) Secretariat | CNC | 0 | General State Budget | bar: 1 Quarter Mar to 2 Quarter Apr
|  |  | Output - Timely publication of the annual reports of the EITI-AO based on the EITI requirements. | 32 | Conduct of training for the Secretariat and the Independent Administrator on planning and delivery of Requirement 4 - Design and conclusion of formats of reports and preparation of the first EITI-AO Report | [48 empty] | NCC(MSG) Secretariat) | CNC | 22346 | General State Budget | bar: 2 Quarter May; 1 Quarter Jan to 1 Quarter Feb
|  |  |  | 33 | Contracting and appointment of the Independent Administrator for the 1st EITI-AO Report | [48 empty] | NCC(MSG) Secretariat) | CNC | 185600 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan to 1 Quarter Mar
|  |  |  | 34 | Contracting of technical, legal and communication consultant | [48 empty] | NCC(MSG) Secretariat |  | 120567 | General State Budget | bar: 3 Quarter July; 1 Quarter Jan to 1 Quarter Mar
|  |  |  | 35 | Training for companies, Government and members of the MSG involved in payments and collection of revenues on models for completion of date to be included in the EITI-AO Report | [48 empty] | AWG/CNC | AWG/CNC | 64000 | General State Budget | bar: 3 Quarter July; 1 Quarter Mar
|  |  |  | 36 | Exchange visit to the EITI International Secretariat | [48 empty] | NCC(MSG) Secretariat) | CNC | 54398 | General State Budget | bar: 1 Quarter Mar; 3 Quarter Aug; 1 Quarter Mar
|  |  |  | 37 | Presentation, approval and publication of the first EITI-AO Report to the MSG and through briefings/news | [48 empty] | NCC(MSG | MSG | 35200 | General State Budget | bar: 4 Quarter Oct
|  |  |  | 38 | Printing and distribution of the 1st EITI-AO Report | [48 empty] | NCC(MSG) Secretariat | CNC | 13987 | General State Budget | bar: 4 Quarter Nov to 4 Quarter Dec
|  |  |  | 39 | Workshop on lessons to be learned from the 1st EITI-AO Report ( for the relevant stakeholders) | [48 empty] | NCC(MSG | MSG | 26098 | General State Budget | bar: 4 Quarter Nov
|  |  | Output - meetings held throughout the three years. | 40 | Holding of quarterly meetings of the MSG (minimum eight) for evaluation of progress of activities and monitoring the overall performance of the implementation of the EITI in Angola | [48 empty] | NCC(MSG | MSG | 16987 | General State Budget | bar: 1 Quarter Jan; 2 Quarter Apr; 3 Quarter July; 4 Quarter Oct; 1 Quarter Jan; 2 Quarter Jun; 3 Quarter Sep; 4 Quarter Dec; 1 Quarter Mar; 2 Quarter Jun; 4 Quarter Oct to 4 Quarter Nov
|  |  |  | 41 | Organization of field visits to the extractive regions for members of the MSG Secretariat | [48 empty] | NCC(MSG | CNC | 18609 | General State Budget | bar: 1 Quarter Jan; 2 Quarter Apr; 3 Quarter July; 4 Quarter Oct; 1 Quarter Jan; 2 Quarter Jun; 3 Quarter Sep; 4 Quarter Dec; 1 Quarter Mar; 2 Quarter Jun; 4 Quarter Oct to 4 Quarter Nov
TOTAL BUDGET | [55 empty] | 1425337.56
0
Note on AQ4: beatriz catomi:
Note on C8: beatriz catomi:

## Objective 2
WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE - ANGOLA (2022-2024)
OBJECTIVE Nº 2: Enhance and strengthen transparency of management of revenues from the extractive sector, improve the legal and institutional framework and the process of granting contracts and licences
Objective | General EITI Requirements | Overall output | Expected Output | Activity |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | Responsible entity | Responsável | Budget allocation (USD) | Source of Financing
[6 empty] | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter |  |  | 1 Quarter |  |  | 2 Quarter |  |  | 3 Quarter |  |  | 4 Quarter
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Enhance and strengthen transparency of management of revenues from the extractive sector, improve the legal and institutional framework and the process of granting contracts and licences | Requirement 2 Legal and institutional framework, including granting of contracts and licences. (The EITI requirements on transparency of the legal framework and grant of rights of the extractive industries include: (2.1) legal and tax regime; (2.2) grant of contracts and licences; (2.3) register of licences; (2.4) contracts; (2.5) beneficial owners; and (2.6) state participation in the extractive sector.) | Disclosure of how the Extractive Sector is managed, allowing stakeholders to understand the laws and procedures for the allocation of exploration and production rights, the legal, regulatory and contractual framework applicable to the extractive sector and the institutional responsibilities of the State for management of revenues collected from the sector. | Output - Analysis of gaps, legal, regulatory and policy frameworks. | 42 | Investigation, analysis and presentation of information relevant for the Study of the Scope of the Legal Framework and Fiscal Regime, both for mining and oil and gas in Angola, and presentation of the conclusions to the MSG and other key stakeholders (identified). | [48 empty] | Technical Working Group | MSG | 123654 | Other voluntary funding sources | bar: 2 Quarter May to 3 Quarter July; 3 Quarter July
|  |  |  | 43 | Publication of legal, regulatory and policy changes in the EITI-AO website | [48 empty] | NCC(MSG) Secretariat | CNC | 15765 | Other voluntary funding sources | bar: 1 Quarter Mar; 2 Quarter Jun; 3 Quarter Sep; 4 Quarter Dec to 4 Quarter Dec
|  |  | Output - Plan published for the disclosure of contracts and licences and information on beneficial owners. | 44 | Development of a plan for disclosure of contracts, licences and their respective addendums in force in the extractive industries, and information on beneficial owners, in conjunction with Government entities. | [48 empty] | NCC(MSG) Secretariat) | CNC | 57987.91 | General State Budget | bar: 2 Quarter May to 2 Quarter Jun
|  |  |  | 45 | Workshop to present the results | [48 empty] | NCC(MSG) Secretariat | CNC | 12760 | Other voluntary funding sources | bar: 3 Quarter Aug; 4 Quarter Nov
| Requirement 3. Exploration and production. (The EITI requires disclosure of information related to exploration and production, allowing the stakeholders to understand the sector's potential.) | Enhance transparency in order to map operators and investments.
|  |  | Output - Ensuring collection of current data on production, consumption and exports. | 46 | Mapping of production, consumption and export data (oil, gas and mining), including analysis of the creation of a policy on data publication. | [48 empty] | Technical Working Group/Companies in Sector | CNC | 0 | Other voluntary funding sources | bar: 1 Quarter Jan
|  |  |  | 47 | Publication of production, consumption and export data for the triennium 2021- 2023 | [48 empty] | NCC Secretariat/Companies in Sector | CNC | 0 | Other voluntary funding sources | bar: 1 Quarter Feb; 3 Quarter Aug
TOTAL BUDGET | [55 empty] | 210166.91
0
Note on AQ4: beatriz catomi:

## Objective 3
WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE - ANGOLA (2022-2024)
OBJECTIVE Nº 3: Promote the public disclosure of taxes, levies and contributions of the extractive sector, including profits and the process of transfer of revenues to the host communities
Objective | General EITI Requirements | Overall output | Expected Output | Activity |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | Responsible entity | Responsável | Budget allocation (USD) | Source of Financing
[6 empty] | 1 Trimestre |  |  | 2 Trimestre |  |  | 3 Trimestre |  |  | 4 Trimestre |  |  | 1 Trimestre |  |  | 2 Trimestre |  |  | 3 Trimestre |  |  | 4 Trimestre |  |  | 1 Trimestre |  |  | 2 trimestre |  |  | 3 Trimestre |  |  | 4 Trimestre |  |  | 1 Trimestre |  |  | 2 trimestre |  |  | 3 Trimestre |  |  | 4 Trimestre
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Promote the public disclosure of taxes, levies and contributions of the extractive sector, including profits and the process of transfer of revenues to the host communities | Requirement 4. Collection of revenues. (The EITI requires disclosure covering payments of companies and government revenues derived from from the extractive industries) | Publication of information on taxes, levies and contributions collected by the State in the sector, including State participation through state enterprises.
|  |  | Output - Study of the scope of revenues collected in preparation for the first EITI-AO Report. | 48 | Development of Terms of Reference for the Independent Administrator | [48 empty] | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | bar: 3 Trimestre Aug to 4 Trimestre Oct; 1 Trimestre Mar
|  |  |  | 49 | Determination of total revenues of extractive operators to be included in the EITI-AO Report, including breakdown of amounts received and definition of the level of materiality | [48 empty] | Technical Working Group | MSG | 0 | General State Budget | bar: 2 trimestre Apr
|  |  |  | 50 | Presentation of the results and validation together with the MSG | [48 empty] | NCC(MSG) | MSG | 12754 | General State Budget | bar: 2 trimestre Apr
|  |  | Output - Institutionalize the systematic disclosure of data. | 51 | Development of a plan for disclosure of beneficial owners, together with the private sector | [48 empty] | Technical Working Group | CNC | 120324 | General State Budget | bar: 3 Trimestre Aug
|  |  |  | 52 | Creation and mapping of the Flexible Register of Extractive Industries and Definition of the Aggregator/Data Regulator/Information Platform | [48 empty] | Technical Working Group | CNC | 349566.9 | General State Budget | bar: 3 Trimestre Aug to 4 Trimestre Dec
|  |  |  | 53 | Conduct of a study on the participation of state-owned enterprises in the mining and oil sector, including rules and practices prevailing between the Government and state-owned enterprises covering financing and governance. | [48 empty] | NCC(MSG) | MSG | 75765 | Other voluntary funding sources | bar: 4 Trimestre Oct
|  |  |  | 54 | Production of reports on the annual audit of results and the impact of implementaiton of the EITI on the management of mining and oil resources in Angola, including the degere of complaince with the requrements of the EITI Standard | [48 empty] | NCC(MSG) |  | 90234 | General State Budget | bar: 4 Trimestre Oct
|  |  |  | 55 | Promotion of sy8smtematic piblication of data in the EITI-AO reports, in an online open data format, making them uncertdanabkle and accessible to all | [48 empty] | GOV | GOV | 80987 | General State Budget | bar: 2 trimestre Apr
| Requirement 5. Allocation of revenues. (The requirements related to allocaiton of revenues include: (5.1) distribution of revenues; (5.2) subnational transfers; and (5.3) management of revenues and expenditures) | Improve knowledge of the benefits obtained by citizens asa result of investment in the extractuive industruies, ensure greater access to informaiton on the EITI-AO.
|  |  | Output - Ensure collection of data related to allocation of revenues for systematiuc disclosure. | 56 | Monitoring of the process of collection of data on revenues from operations of the extratcive industries for the EITI-AO Report, including any subnaitonal payments (e.g. local royalties). | [48 empty] | NCC Secretariat | CNC | 0 | General State Budget | bar: 2 trimestre Apr
| Requirement 6. Social and economic expenditures (The requirements realted to allocation of revenues include: (6.1) social and environmental expenditures of companies; (6.2) tax-equivalent expenses of state enterprises; (6.3) overview of the contrubution of the extractiveindustruies to the economy; and (6.4) environmental impact of extractuve activities) |  | Output - Better awareness of the impacts of the extratcuve industries leading to better management and accountability for the social and environmentla impacts by those responsible. | 57 | Disclosure of social and environmental expoenditures of the extratcuve comoanies, through the EITI-AO Report (capture of "material", social and environmentalto communities and to the Governmewnt, and informaiton on expoensdiutres related to social responsibiklity and remedial programmes, including "Persons affecrted by the project" (resettlement, etc.) | [48 empty] | Independent Administrator | AI | 0 | General State Budget | bar: 2 trimestre Apr
|  |  |  | 58 | Elaboraiton of a study on energy transition, a concept which has the purpose of replacing the use of finite soruces prejudicial to the environment, such as fossil fuels, with renewabe soruces, such as solar, biogas. and wind. | [48 empty] | Ministry of Energy, MCTA |  | 15876.98 | Other voluntary funding sources | bar: 2 trimestre Apr
|  |  |  | 59 | Analysis of the contri0bution of the extrative sectot to the economy (for eample, size of the extractive sect-or in realtion to GDP and the rest of the economy, revenues, exports and employment generated in abolsute and relative terms (%); and monioting of the activity to develoa "contribution mointoring tool" to see i0f the extractive contribution is as expected. | [48 empty] | Independent Administrator | AI | 0 | General State Budget | bar: 1 Trimestre Mar to 2 trimestre Apr
| Requirement 7. Outcomes and impact. 7.1 Public debate |  | Output- Ensure management of the expectations of the population and society at large, and better accountability for the management of revenues from the sector. | 60 | Publication of the results and recommendations of the EITI-AO Report to society and use of social communication media. Publicaiton of the first EITI-AO Report. | [48 empty] | CSO | OSC | 40987 | General State Budget | bar: 2 trimestre Apr to 4 Trimestre Dec
|  |  | Output - Conduct of four field visits | 61 | Publication of the results and recommendations of the EITI-AO Report to communities where the projects are located. | [48 empty] | CSO | OSC | 190254 | Other voluntary funding sources | bar: 2 trimestre Apr; 4 Trimestre Nov to 4 Trimestre Dec
| 7.2 Accessibiity of data and open data |  | Output- Improve the level of access to information in the extractive sector in Angola. | 62 | Definition of the NCC Communicaiton Policy (creation of scope of the EITI-AO, to faciliate cmmunication, creation of logo) | [48 empty] | NCC(MSG) Secretariat) | CNC | 97468.98 | Other voluntary funding sources | bar: 2 Trimestre Apr
|  |  |  | 63 | Creation, maintenance and uopdate of EITI-AO website | [48 empty] | NCC(MSG) Secretariat) | CNC | 346127.98 | Other voluntary funding sources | bar: 4 Trimestre Nov
ORÇAMENTO TOTAL | [55 empty] | 1420345.84
0
Note on AQ4: beatriz catomi:

## General financing plan
FINANCING PLAN OF THE WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE OF EITI- ANGOLA (2022-2024)
Activity |  |  |  |  | Responsible entity | Responsible | Budget allocation (USD) | Source of Financing
|  | 2022 | 2023 | 2024
1 | Statement by His Excellency, the President of the Republic of Angola expressing his interest in adhesion to the EITI | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
2 | Opening ceremony of the new MSG | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
3 | Publication of list of the new members of the MSG as signatories (post-election) | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
4 | Signing of Memorandum of Understanding between the Government stakeholders on the implementation of the EITI | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC/GOV | 0 | General State Budget | 0
5 | Annual quota to the EITI International Secretariat | 10000 | 10000 | 10000 | NCC(MSG) Secretariat |  | 30000 | General State Budget | 0
0
6 | Constitution of the EITI-AO National Secretariat | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
7 | Creation of the functional structure of the administrative organization of the NCC, with rules of procedure | 37987.98 | 27266.02 | 0 | NCC(MSG) Secretariat | CNC | 65254 | General State Budget | 0
8 | Technical resources, logistical support for the functioning of the NCC Secretariat | 120442.54 | 116558.44 | 17876 | NCC(MSG) Secretariat |  | 254876.98 | General State Budget | 0
9 | Logistical support for the holding of meetings and travel within Angola | 10995.68 | 10995 | 10997 | NCC(MSG) Secretariat |  | 32987.68 | Other voluntary funding sources | 0
10 | Provision of administrative service to support the functioning of the NCC Secretariat | 96000 | 96000 | 96000 | NCC(MSG) Secretariat |  | 288000 | General State Budget | 0
0
11 | Definition of the financing model for activities to be executed by the NCC, including mapping of sources of financing | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
12 | Elaboration and update of the Terms of Reference on the National Secretariat | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
13 | Consultation and approval of the operational documents and procedures by the MSG | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
0
14 | Mapping of the MSG member base (level of entity) and disclosure (Private Sector, Government and CSOs) | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
15 | Ensure and support CSOs and the private sector in the development of transparent electoral procedures | 2920 | 2920 | 2920 | NCC/Private Sector /CSO Secretariat | CNC/SP/OSC | 8760 | Other voluntary funding sources | 0
16 | Holding of elections for the industry and civil society and present the Government representatives | 0 | 0 | 0 | CSO & Private Sector | OSC & SP | 0 | General State Budget | 0
17 | Monitoring of the electoral process, registration and publication of the process | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
18 | Nomination of the NCC (MSG), Chairperson and Executive Director | 0 | 0 | 0 | GOV | GOV | 0 | General State Budget | 0
19 | Identifying of new members of the Working Group | 0 | 0 | 0 | NCC(MSG) Secretariat | MSG | 0 | General State Budget | 0
0
20 | Induction training on key question of implementation of the EITI (taxation, fiscal regime , etc.) | 21876.98 | 11754.51 | 11754.51 | NCC(MSG) Secretariat | CNC | 45386 | General State Budget | 0
21 | Exchange of experiences with other EITI implementing countries (e.g.. Mozambique) | 12658 | 12658 | 12660 | NCC(MSG) Secretariat | CNC | 37976 | General State Budget | 0
22 | Participation of the NCC ( MSG) on the Oil and Gas Mining Conference (INDABA 2022-2023) | 14382.5 | 14382.5 | 0 | NCC(MSG) Secretariat | CNC | 28765 | General State Budget | 0
23 | Organization of strategic meetings for members of the MSG, to promote better coordination and information flows. | 1195 | 1195 | 1197 | NCC(MSG) Secretariat | MSG | 3587 | Other voluntary funding sources | 0
24 | Conduct of a study to identify possible obstacles to the implementation of the EITI in Angola and strategies to mitigate risks | 46787.76 | 7199.24 | 0 | NCC(MSG) Secretariat | MSG | 53987 | General State Budget | 0
0
25 | Elaboration of Annual Plans of Activities for the triennium 2021 - 2023 | 525 | 525 | 525 | NCC(MSG) | MSG | 1575 | Other funding sources | 0
26 | Annual Report of Activities 2021 and elaboration of the Annual Plan 2022 | 6438.45 | 6438.45 | 0 | NCC(MSG | MSG | 12876.9 | Other voluntary funding sources | 0
27 | Annual Report of Activities 2022 and elaboration of the Annual Plan 2023 | 0 | 878.5 | 878.5 | NCC(MSG | MSG | 1757 | Other voluntary funding sources | 0
28 | Annual Report of Activities 2023 | 0 | 878.5 | 878.5 | NCC(MSG | MSG | 1757 | Other voluntary funding sources | 0
0
29 | Preparation for submission of the Candidature to the EITI International Board | 0 | 0 | 0 | NCC(MSG | CNC | 0 | General State Budget | 0
30 | Organization of supporting documentation to be annexed to Angola's candidature for the EITI to be presented to the MSG | 0 | 0 | 0 | NCC(MSG | MSG | 0 | General State Budget | 0
31 | Submission of candidature to the EITI International Board | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
0
32 | Conduct of training for the Secretariat and the Independent Administrator on planning and delivery of Requirement 4 - Design and conclusion of formats of reports and preparation of the first EITI-AO Report | 11173 | 11173 | 0 | NCC(MSG) Secretariat) | CNC | 22346 | General State Budget | 0
33 | Contracting and appointment of the Independent Administrator for the 1st EITI-AO Report | 92800 | 92800 | 0 | NCC(MSG) Secretariat) | CNC | 185600 | General State Budget | 0
34 | Contracting of technical, legal and communication consultant | 40189 | 40189 | 40189 | NCC(MSG) Secretariat |  | 120567 | General State Budget | 0
35 | Training for companies, Government and members of the MSG involved in payments and collection of revenues on models for completion of date to be included in the EITI-AO Report | 22333 | 21491 | 20176 | AWG/CNC | AGT/CNC | 64000 | General State Budget | 0
36 | Exchange visit to the EITI International Secretariat | 38765 | 15633 | 0 | NCC(MSG) Secretariat) | CNC | 54398 | General State Budget | 0
37 | Presentation, approval and publication of the first EITI-AO Report to the MSG and through briefings/news | 0 | 17600 | 17600 | NCC(MSG | MSG | 35200 | General State Budget | 0
38 | Printing and distribution of the 1st EITI-AO Report | 0 | 6993.5 | 6993.5 | NCC(MSG) Secretariat | CNC | 13987 | General State Budget | 0
39 | Workshop on lessons to be learned from the 1st EITI-AO Report ( for the relevant stakeholders) | 8699 | 8699 | 8700 | NCC(MSG | MSG | 26098 | General State Budget | 0
40 | Holding of quarterly meetings of the MSG (minimum eight) for evaluation of progress of activities and monitoring the overall performance of the implementation of the EITI in Angola | 5622 | 5622 | 5743 | NCC(MSG | MSG | 16987 | General State Budget | 0
41 | Organization of field visits to the extractive regions for members of the MSG Secretariat | 6203 | 6203 | 6203 | NCC(MSG | CNC | 18609 | General State Budget | 0
0
42 | Investigation, analysis and presentation of information relevant for the Study of the Scope of the Legal Framework and Fiscal Regime, both for mining and oil and gas in Angola, and presentation of the conclusions to the MSG and other key stakeholders (identified). | 97659.76 | 25994.24 | 0 | Technical Working Group | MSG | 123654 | Other voluntary funding sources | 0
43 | Publication of legal, regulatory and policy changes in the EITI-AO website | 5255 | 5255 | 5255 | NCC(MSG) Secretariat | CNC | 15765 | Other voluntary funding sources | 0
0
44 | Development of a plan for disclosure of contracts, licences and their respective addendums in force in the extractive industries, and information on beneficial owners, in conjunction with Government entities. | 5497.91 | 33160 | 19330 | NCC(MSG) Secretariat) | CNC | 57987.91 | General State Budget | 0
45 | Workshop to present the results | 2831.1 | 6380 | 3548.9 | NCC(MSG) Secretariat | CNC | 12760 | Other voluntary funding sources | 0
0
46 | Mapping of production, consumption and export data (oil, gas and mining), including analysis of the creation of a policy on data publication. | 0 | 0 | 0 | Technical Working Group/Companies in Sector | CNC | 0 | Other voluntary funding sources | 0
47 | Publication of production, consumption and export data for the triennium 2021- 2023 | 0 | 0 | 0 | NCC Secretariat/Companies in Sector | CNC | 0 | Other voluntary funding sources | 0
0
48 | Development of Terms of Reference for the Independent Administrator | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
49 | Determination of total revenues of extractive operators to be included in the EITI-AO Report, including breakdown of amounts received and definition of the level of materiality | 0 | 0 | 0 | Technical Working Group | MSG | 0 | General State Budget | 0
50 | Presentation of the results and validation together with the MSG | 0 | 6377 | 6377 | NCC(MSG) | MSG | 12754 | General State Budget | 0
0
51 | Development of a plan for disclosure of beneficial owners, together with the private sector | 52987.76 | 38688.12 | 28648.12 | Technical Working Group | CNC | 120324 | General State Budget | 0
52 | Creation and mapping of the Flexible Register of Extractive Industries and Definition of the Aggregator/Data Regulator/Information Platform | 194783.45 | 81795.69 | 72987.76 | Technical Working Group | CNC | 349566.9 | General State Budget | 0
53 | Conduct of a study on the participation of state-owned enterprises in the mining and oil sector, including rules and practices prevailing between the Government and state-owned enterprises covering financing and governance. | 56898.98 | 18866.02 | 0 | NCC(MSG) | MSG | 75765 | Other voluntary funding sources | 0
54 | Production of reports on the annual audit of results and the impact of implementation of the EITI on the management of mining and oil resources in Angola, including the degree of compliance with the requirements of the EITI Standard | 0 | 45117 | 45117 | NCC(MSG) |  | 90234 | General State Budget | 0
55 | Promotion of systematic publication of data in the EITI-AO reports, in an online open data format, making them understandable and accessible to all | 0 | 40493.5 | 40493.5 | GOV | GOV | 80987 | General State Budget | 0
0
56 | Monitoring of the process of collection of data on revenues from operations of the extractive industries for the EITI-AO Report, including any subnational payments (e.g. local royalties). | 0 | 0 | 0 | NCC Secretariat | CNC | 0 | General State Budget | 0
0
57 | Disclosure of social and environmental expenditures of the extractive companies, through the EITI-AO Report (capture of "material", social and environmental to communities and to the Government, and information on expenditures related to social responsibility and remedial programmes, including "Persons affected by the project" (resettlement, etc.) | 0 | 0 | 0 | Independent Administrator | AI | 0 | General State Budget | 0
58 | Elaboration of a study on energy transition, a concept which has the purpose of replacing the use of finite sources prejudicial to the environment, such as fossil fuels, with renewable sources, such as solar, biogas. and wind. | 0 | 9764 | 6112.98 | Ministry of Energy, MCTA |  | 15876.98 | Other voluntary funding sources | 0
59 | Analysis of the contribution of the extractive sector to the economy (for example, size of the extractive sect-or in relation to GDP and the rest of the economy, revenues, exports and employment generated in absolute and relative terms (%); and monitoring of the activity to develop "contribution monitoring tool" to see of the extractive contribution is as expected. | 0 | 0 | 0 | Independent Administrator | AI | 0 | General State Budget | 0
60 | Publication of the results and recommendations of the EITI-AO Report to society and use of social communication media. Publication of the first EITI-AO Report. |  |  |  | CSO | OSC | 40987 | General State Budget
|  | 0 | 20493.5 | 20493.5 |  |  |  |  | 0
61 | Publication of the results and recommendations of the EITI-AO Report to communities where the projects are located. |  |  |  | CSO | OSC | 190254 | Other voluntary funding sources
|  | 0 | 95127 | 95127 |  |  |  |  | 0
62 | Definition of the NCC Communication Policy (creation of scope of the EITI-AO, to facilitate communication, creation of logo) | 48734.49 | 38654.87 | 10079.62 | NCC(MSG) Secretariat) | CNC | 97468.98 | Other voluntary funding sources | 0
63 | Creation, maintenance and update of EITI-AO website | 287659.76 | 48462.22 | 10006 | NCC(MSG) Secretariat) | CNC | 346127.98 | Other voluntary funding sources | 0
TOTAL BUDGET |  | 1360302.1 | 1060680.82 | 634867.39 |  |  | 3055850.31
3055850.31

## State Budget financing plan
FINANCING PLAN OF THE WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE OF EITI- ANGOLA (2022-2024)
70 % OF NCC(MSG) WORK PLAN OF FINANCED BY THE GENERAL STATE BUDGET
Activity |  |  |  |  | Responsible entity | Responsible | Budget allocation (USD) | Source of Financing
|  | 2022 | 2023 | 2024
1 | Statement by His Excellency, the President of the Republic of Angola expressing his interest in adhesion to the EITI | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
2 | Opening ceremony of the new MSG | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
3 | Publication of list of the new members of the MSG as signatories (post-election) | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
4 | Signing of Memorandum of Understanding between the Government stakeholders on the implementation of the EITI | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC/GOV | 0 | General State Budget | 0
5 | Annual quota to the EITI International Secretariat | 10000 | 10000 | 10000 | NCC(MSG) Secretariat |  | 30000 | General State Budget | 0
0
6 | Constitution of the EITI-AO National Secretariat | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
7 | Creation of the functional structure of the administrative organization of the NCC, with rules of procedure | 37987.98 | 27266.02 | 0 | NCC(MSG) Secretariat | CNC | 65254 | General State Budget | 0
8 | Technical resources, logistical support for the functioning of the NCC Secretariat | 120442.54 | 116558.44 | 17876 | NCC(MSG) Secretariat) |  | 254876.98 | General State Budget | 0
10 | Provision of administrative service to support the functioning of the NCC Secretariat | 96000 | 96000 | 96000 | NCC(MSG) Secretariat |  | 288000 | General State Budget | 0
0
11 | Definition of the financing model for activities to be executed by the NCC, including mapping of sources of financing | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
12 | Elaboration and update of the Terms of Reference on the National Secretariat | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
13 | Consultation and approval of the operational documents and procedures by the MSG | 0 | 0 | 0 | NCC(MSG) Secretariat | CNC | 0 | General State Budget | 0
0
14 | Mapping of the MSG member base (level of entity) and disclosure (Private Sector, Government and CSOs) | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
16 | Holding of elections for the industry and civil society and present the Government representatives | 0 | 0 | 0 | CSO & Private Sector | OSC & SP | 0 | General State Budget | 0
17 | Monitoring of the electoral process, registration and publication of the process | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
18 | Nomination of the NCC (MSG), Chairperson and Executive Director | 0 | 0 | 0 | GOV | GOV | 0 | General State Budget | 0
19 | Identifying of new members of the Working Group | 0 | 0 | 0 | NCC(MSG) Secretariat) | MSG | 0 | General State Budget | 0
0
20 | Induction training on key question of implementation of the EITI (taxation, fiscal regime , etc.) | 21876.98 | 11754.51 | 11754.51 | NCC(MSG) Secretariat) | CNC | 45386 | General State Budget | 0
21 | Exchange of experiences with other EITI implementing countries (e.g.. Mozambique) | 12658 | 12658 | 12660 | NCC(MSG) Secretariat) | CNC | 37976 | General State Budget | 0
22 | Participation of the NCC ( MSG) on the Oil and Gas Mining Conference (INDABA 2022-2023) | 14382.5 | 14382.5 | 0 | NCC(MSG) Secretariat) | CNC | 28765 | General State Budget | 0
23 | Organization of strategic meetings for members of the MSG, to promote better coordination and information flows. | 46787.76 | 7199.24 | 0 | NCC(MSG) Secretariat) | MSG | 53987 | General State Budget | 0
24 | Conduct of a study to identify possible obstacles to the implementation of the EITI in Angola and strategies to mitigate risks | [7 empty] | 0
29 | Preparation for submission of the Candidature to the EITI International Board | 0 | 0 | 0 | NCC(MSG) | CNC | 0 | General State Budget | 0
30 | Organization of supporting documentation to be annexed to Angola's candidature for the EITI to be presented to the MSG | 0 | 0 | 0 | NCC(MSG) | MSG | 0 | General State Budget | 0
31 | Submission of candidature to the EITI International Board | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
0
32 | Conduct of training for the Secretariat and the Independent Administrator on planning and delivery of Requirement 4 - Design and conclusion of formats of reports and preparation of the first EITI-AO Report | 11173 | 11173 | 0 | NCC(MSG) Secretariat) | CNC | 22346 | General State Budget | 0
33 | Contracting and appointment of the Independent Administrator for the 1st EITI-AO Report | 92800 | 92800 | 0 | NCC(MSG) Secretariat) | CNC | 185600 | General State Budget | 0
34 | Contracting of technical, legal and communication consultant | 40189 | 40189 | 40189 | NCC(MSG) Secretariat) |  | 120567 | General State Budget | 0
35 | Training for companies, Government and members of the MSG involved in payments and collection of revenues on models for completion of date to be included in the EITI-AO Report | 22333 | 21491 | 20176 | AWG/CNC | AWG/CNC | 64000 | General State Budget | 0
36 | Exchange visit to the EITI International Secretariat | 38765 | 15633 | 0 | NCC(MSG) Secretariat) | CNC | 54398 | General State Budget | 0
37 | Presentation, approval and publication of the first EITI-AO Report to the MSG and through briefings/news | 0 | 17600 | 17600 | NCC(MSG) | MSG | 35200 | General State Budget | 0
38 | Printing and distribution of the 1st EITI-AO Report | 0 | 6993.5 | 6993.5 | NCC(MSG) Secretariat) | CNC | 13987 | General State Budget | 0
39 | Workshop on lessons to be learned from the 1st EITI-AO Report ( for the relevant stakeholders) | 8699 | 8699 | 8700 | NCC(MSG)) | MSG | 26098 | General State Budget | 0
40 | Holding of quarterly meetings of the MSG (minimum eight) for evaluation of progress of activities and monitoring the overall performance of the implementation of the EITI in Angola | 5622 | 5622 | 5743 | NCC(MSG) | MSG | 16987 | General State Budget | 0
41 | Organization of field visits to the extractive regions for members of the MSG Secretariat | 6203 | 6203 | 6203 | NCC(MSG) | CNC | 18609 | General State Budget | 0
0
44 | Development of a plan for disclosure of contracts, licences and their respective addendums in force in the extractive industries, and information on beneficial owners, in conjunction with Government entities. | 5497.91 | 33160 | 19330 | NCC(MSG) Secretariat) | CNC | 57987.91 | General State Budget | 0
0
48 | Development of Terms of Reference for the Independent Administrator | 0 | 0 | 0 | NCC(MSG) Secretariat) | CNC | 0 | General State Budget | 0
49 | Determination of total revenues of extractive operators to be included in the EITI-AO Report, including breakdown of amounts received and definition of the level of materiality | 0 | 0 | 0 | Technical Working Group | MSG | 0 | General State Budget | 0
50 | Presentation of the results and validation together with the MSG | 0 | 6377 | 6377 | NCC(MSG) | MSG | 12754 | General State Budget | 0
0
51 | Development of a plan for disclosure of beneficial owners, together with the private sector | 52987.76 | 38688.12 | 28648.12 | Technical Working Group | CNC | 120324 | General State Budget | 0
52 | Creation and mapping of the Flexible Register of Extractive Industries and Definition of the Aggregator/Data Regulator/Information Platform | 194783.45 | 81795.69 | 72987.76 | Technical Working Group | CNC | 349566.9 | General State Budget | 0
53 | Conduct of a study on the participation of state-owned enterprises in the mining and oil sector, including rules and practices prevailing between the Government and state-owned enterprises covering financing and governance. | 0 | 45117 | 45117 | NCC(MSG) |  | 90234 | General State Budget | 0
54 | Production of reports on the annual audit of results and the impact of implementation of the EITI on the management of mining and oil resources in Angola, including the degree of compliance with the requirements of the EITI Standard | 0 | 40493.5 | 40493.5 | GOV | GOV | 80987 | General State Budget | 0
55 | Promotion of systematic publication of data in the EITI-AO reports, in an online open data format, making them understandable and accessible to all | [7 empty] | 0
56 | Monitoring of the process of collection of data on revenues from operations of the extractive industries for the EITI-AO Report, including any subnational payments (e.g. local royalties). | 0 | 0 | 0 | NCC Secretariat | CNC | 0 | General State Budget | 0
0
57 | Disclosure of social and environmental expenditures of the extractive companies, through the EITI-AO Report (capture of "material", social and environmental to communities and to the Government, and information on expenditures related to social responsibility and remedial programmes, including "Persons affected by the project" (resettlement, etc.) | 0 | 0 | 0 | Independent Administrator | AI | 0 | General State Budget | 0
59 | Analysis of the contribution of the extractive sector to the economy (for example, size of the extractive sect-or in relation to GDP and the rest of the economy, revenues, exports and employment generated in absolute and relative terms (%); and monitoring of the activity to develop "contribution monitoring tool" to see of the extractive contribution is as expected. | 0 | 0 | 0 | Independent Administrator | AI | 0 | General State Budget | 0
60 | Publication of the results and recommendations of the EITI-AO Report to society and use of social communication media. Publication of the first EITI-AO Report. |  |  |  | CSO | OSC | 40987 | General State Budget
|  | 0 | 20493.5 | 20493.5 |  |  |  |  | 0
TOTAL BUDGET |  | 839188.88 | 788347.02 | 487341.89 |  |  | 2114877.79
2114877.79

## Other sources financing plan
FINANCING PLAN OF THE WORK PLAN OF THE NATIONAL COORDINATION COMMITTEE OF EITI- ANGOLA (2022-2024)
70 % OF NCC(MSG) WORK PLAN OF FINANCED FROM VOLUNTARY SOURCES
Activity |  |  |  |  | Responsible entity | Responsible | Budget allocation (USD) | Source of Financing
|  | 2022 | 2023 | 2024
9 | Logistical support for the holding of meetings and travel within Angola | 10995.68 | 10995 | 10997 | NCC(MSG) Secretariat |  | 32987.68 | Other voluntary financing sources | 0
15 | Ensure and support CSOs and the private sector in the development of transparent electoral procedures | 2920 | 2920 | 2920 | NCC/private sector/CSO Secretariat | CNC/SP/OSC | 8760 | Other voluntary financing sources | 0
23 | Organization of strategic meetings for members of the MSG, to promote better coordination and information flows. | 1195 | 1195 | 1197 | NCC(MSG) Secretariat | MSG | 3587 | Other voluntary financing sources | 0
0
25 | Elaboration of Annual Plans of Activities for the triennium 2021 - 2023 | 525 | 525 | 525 | NCC(MSG) | MSG | 1575 | Other voluntary financing sources | 0
26 | Annual Report of Activities 2021 and elaboration of the Annual Plan 2022 | 6438.45 | 6438.45 | 0 | NCC(MSG) | MSG | 12876.9 | Other financing sources | 0
27 | Annual Report of Activities 2022 and elaboration of the Annual Plan 2023 | 0 | 878.5 | 878.5 | NCC(MSG) | MSG | 1757 | Other voluntary financing sources | 0
28 | Annual Report of Activities 2023 | 0 | 878.5 | 878.5 | NCC(MSG) | MSG | 1757 | Other voluntary financing sources | 0
0
42 | Investigation, analysis and presentation of information relevant for the Study of the Scope of the Legal Framework and Fiscal Regime, both for mining and oil and gas in Angola, and presentation of the conclusions to the MSG and other key stakeholders (identified). | 97659.76 | 25994.24 | 0 | Technical Working Group | MSG | 123654 | Other voluntary financing sources | 0
43 | Publication of legal, regulatory and policy changes in the EITI-AO website | 5255 | 5255 | 5255 | NCC(MSG) Secretariat | CNC | 15765 | Other voluntary financing sources | 0
0
45 | Workshop to present the results | 2831.1 | 6380 | 3548.9 | NCC(MSG) Secretariat | CNC | 12760 | Other voluntary financing sources | 0
0
46 | Mapping of production, consumption and export data (oil, gas and mining), including analysis of the creation of a policy on data publication. | 0 | 0 | 0 | Technical Working Group/Companies in the sector | CNC | 0 | Other voluntary financing sources | 0
47 | Publication of production, consumption and export data for the triennium 2021- 2023 | 0 | 0 | 0 | NCC Secretariat/Companies in the sector | CNC | 0 | Other voluntary financing sources | 0
0
53 | Conduct of a study on the participation of state-owned enterprises in the mining and oil sector, including rules and practices prevailing between the Government and state-owned enterprises covering financing and governance. | 56898.98 | 18866.02 | 0 | NCC(MSG) | MSG | 75765 | Other voluntary financing sources | 0
58 | Elaboration of a study on energy transition, a concept which has the purpose of replacing the use of finite sources prejudicial to the environment, such as fossil fuels, with renewable sources, such as solar, biogas. and wind. | 0 | 9764 | 6112.98 | Ministry of Energy and MCTA |  | 15876.98 | Other voluntary financing sources | 0
61 | Publication of the results and recommendations of the EITI-AO Report to communities where the projects are located. |  |  |  | CSO | OSC | 190254 | Other voluntary financing sources
|  | 0 | 95127 | 95127 |  |  |  |  | 0
62 | Definition of the NCC Communication Policy (creation of scope of the EITI-AO, to facilitate communication, creation of logo) | 48734.49 | 38654.87 | 10079.62 | NCC(MSG) Secretariat | CNC | 97468.98 | Other voluntary financing sources | 0
63 | Creation, maintenance and update of EITI-AO website | 287659.76 | 48462.22 | 10006 | NCC(MSG) Secretariat | CNC | 346127.98 | Other voluntary financing sources | 0
TOTAL BUDGET |  | 521113.22 | 272333.8 | 147525.5 |  |  | 940972.52
940972.52

## Budget summary 2022-2024
PROVISIONAL BUDGET 2022 - 2024
| USD |  |  | 641
|  | 2022 | 2023 | 2024 | Grand Total | Total %
| Descrição | Annual
Revenues/Financing
External
| Other voluntary funding sources | 376698.67 | 320876.98 | 243396.87 | 940972.52 | 30.7925 | 940972.52
| General Budget of the State | 976876.34 | 765498.76 | 372502.69 | 2114877.79 | 69.2075 | 2114877.79
Other revenues
| Total Revenues | 1353575.01 | 1086375.74 | 615899.56 | 3055850.31 | 100
Costs
| Provision of goods and services | 1328810.76 | 1075765.34 | 604876.89 | 3009452.99 | 99.013 | 952112.09
| Capital expenditures |  |  | 0 | 0 | 0
| Transfer to EITI (Quotas) | 10000 | 10000 | 10000 | 30000 | 0.98702 | 10000
| Tax charges | 0 | 0 | 0 | 0 | 0 | 962112.09
| Total Costs | 1338810.76 | 1085765.34 | 614876.89 | 3039452.99 | 100
| Operating results ( EBITDA ) | 14764.25 | 610.4 | 1022.67 | 16397.32 | 0

## Breakdown State budget expendit
NATUREZA PREVISIONAL DAS DESPESAS OGE
| 2022 | 2023 | 2024 | Total Geral | Total %
Descrição | Anual
Despesas
1.Fornecimentos de Bens e Serviços | 952112 | 754888 | 361480 | 2068480 | 98.5704
2.Despesas de capital
Transferencia para ITIE (Quotas) | 10000 | 10000 | 10000 | 30000 | 1.4296
Encargos Para Fiscais
Total despesas | 962112 | 764888 | 371480 | 2098480 | 100

## Plano de Actividades ITIE-2021 (hidden)
PLANO DE TRABALHO DO COMITE NACIONAL DE COORDENAÇÃO DA ITIE- ANGOLA (2021-2023)
Objetivo | Requisitos do Padrão da ITIE | Resultado Esperado | Output | Actividade |  | 2021 | [11 empty] | Responsável | Responsável | Atribuição de Orçamento (USD) | Agência de Financiamento
[6 empty] | 1 Trimestre |  |  | 2 Trimestre |  |  | 3 Trimestre |  |  | 4 Trimestre
[6 empty] | Jan | Fev. | Mar | Abr. | Mai. | Jun. | Juli | Ago | Set | Out | Nov. | Dez
Criar Capacidade Técnica e Operacional do Comité Nacional de Coordenação e do Secretariado Nacional de modo a Viabilizar a Implementação Efetiva da ITIE em Angola | 1. Supervisão efetiva por parte do Grupo Multipartite (A ITIE exige a supervisão efetiva pelas diversas partes envolvidas. Os principais elementos relacionados à supervisão pelo grupo multipartite incluem: (1.1) o compromisso do governo; (1.2) o envolvimento das empresas; (1.3) o envolvimento da sociedade civil; (1.4) o estabelecimento e o funcionamento de um grupo multipartite; e (1.5) um plano de trabalho acordado com objetivos claros para a implementação da EITI e um cronograma alinhado com os prazos estabelecidos pelo Comitê Diretor da ITIE) | Assegurar o compromisso do governo e o envolvimento da sociedade civil, o estabelecimento e funcionamento de um grupo de múltiplas partes interessadas, um plano de trabalho acordado, objetivos claros e um calendário realista, alinhado com os prazos estabelecidos pelo conselho da ITIE e aumentar do conhecimento dos membros do MSG | Output - Compromisso Governamental dos Princípios e Normas da ITIE | 1 | Declaração de Sua Excelência o Presidente da Republica de Angola manifestando interesse na aderência a ITIE | [12 empty] | Secretariado CNC | CNC | 0 | OGE | bar: 1 Trimestre Fev.
|  |  |  | 2 | Evento de abertura de Cerimónia para o novo MSG | [12 empty] | Secretariado CNC | CNC | 0 | OGE | bar: 1 Trimestre Mar
|  |  |  | 3 | Publicação da carta com todos os Novos Membros do MSG como Signatários (Pós-eleição) | [12 empty] | Secretariado CNC | CNC | 0 | OGE | bar: 2 Trimestre Abr.
|  |  |  | 4 | Assinar Memorando de Entendimento entre as Partes Interessadas do Governo para a implementação da ITIE | [12 empty] | Secretaraido CNC/GOV | CNC/GOV | 0 | OGE | bar: 2 Trimestre Mai.
|  |  | Output-Criar os procedimentos operacionais administrativos e organizativo da ITIE-AO | 5 | Constituição do Secretariado Nacional da ITIE-AO | [12 empty] | Secretariado CNC | CNC | 0 | MIREMPET | bar: 3 Trimestre Juli
|  |  |  | 6 | Criação da estrutura de funcionamento da organização administrativa do CNC, com normas procedimentos | [12 empty] | Secretariado CNC | CNC | 157654 | MIREMPET | bar: 3 Trimestre Juli
|  |  |  | 7 | Meios técnicos, logísticos de suporte ao funcionamento do Secretariado da CNC | [12 empty] | Secretariado CNC |  | 487654 | OGE | bar: 3 Trimestre Juli
|  |  |  | 8 | Remuneração dos colaboradores afectros aos ao Secretariado do CNC | [12 empty] | Secretariado CNC |  | 288000 | MIREMPET | bar: 3 Trimestre Juli to 4 Trimestre Dez
|  |  |  | 9 | Definição do modelo de financiamento das actividades a executar pelo CNC incluindo o mapeamento das fontes de financiamento | [12 empty] | Secretariado CNC | CNC | 0 | MIREMPET | bar: 3 Trimestre Juli
|  |  |  | 10 | Elaboração dos Termos de Referencia do Secretariado Nacional e actualização | [12 empty] | Secretariado CNC | CNC | 0 | MIREMPET | bar: 3 Trimestre Juli
|  |  |  | 11 | Consulta e aprovação de documentos e procedimentos operacionais por parte do MSG | [12 empty] | Secretariado CNC | CNC | 0 | MIREMPET | bar: 3 Trimestre Juli
|  |  |  | 12 | Mapeamento da base de membros do MSG (nível de entidade) e divulgar (Sector Privado, Governo e OSCs) | [12 empty] | Secretariado CNC | CNC | 0 | MIREMPET | bar: 3 Trimestre Set
|  |  |  | 13 | Garantir e apoiar as OSCs e o Sector Privado a desenvolverem procedimentos eleitorais transparentes | [12 empty] | Secreta.CNC/SP/OSC | CNC/SP/OSC | 8760 | MIREMPET | bar: 2 Trimestre Mai.
|  |  |  | 14 | Realização de eleições para a indústria e a sociedade civil e apresentar os representantes do Governo | [12 empty] | OSC & SP | OSC & SP | 0 | MIREMPET | bar: 2 Trimestre Mai.
|  |  |  | 15 | Monitorização do processo eleitoral, registo e divulgação do processo | [12 empty] | Secretariado CNC | CNC | 0 | MIREMPET | bar: 2 Trimestre Mai.
|  |  |  | 16 | Nomeação do CNC (MSG), Presidente e Co-Presidente | [12 empty] | GOV | GOV | 0 | MIREMPET | bar: 2 Trimestre Mai.
|  |  |  | 17 | Identificação de novos membros do Grupo de Trabalho | [12 empty] | Secretariado CNC | MSG | 0 | MIREMPET
ORCAMENTO TOTAL | [19 empty] | 942068
942068